## Sheet1
Task | Time Period | Work Percentage | [10 empty] | Status | Remaining Percentage | Total Percentage
Data Gathering and Idea Presentation | 15 Aug 2023 to 22 Sep | 10% | [10 empty] | Completed | 0% | 10%
Selected Idea Data Gathering | 23 Sep 2023 to 25 Nov |  | 15% | [9 empty] | Completed | 0% | 15%
Website | Dec to still continue |  |  | 15% | 5% | [7 empty] | 15% | 5% | 20%
Model Working | Dec to 10 Jan |  |  |  |  | 12% | 3% | [5 empty] | 12% | 3% | 15%
SRS and SDS Submission | 10Jan to 27 Feb | [6 empty] | 20% |  |  |  |  | Completed |  | 20%
Refrences(Research Paper data adding) | 01 Oct still continue | [7 empty] | 5% | 5% |  |  | 5% | 5% | 10%
Final Thesis | Jan still cotinue | [9 empty] | 5% | 5% | 5% | 5% | 10%